## Slide 1
ASANA WORKFLOW SPECIALIST CAPSTONE
Phoenix Airlines: governed request-to-delivery
Two connected workflows make intake, decisions, delivery, and adoption visible.
Portfolio case study • Jayson • 25 August 2026
01
Deadline-bound launch
02
Ongoing request workflow
03
Deployment and proof
01
Notes: Open with the operating problem and explain that all results shown are design outputs or proposed targets, not claimed production outcomes.
[Sources]
- Phoenix Airlines discovery_asana.docx (user-supplied)
- Biometric Boarding and Security Project.xlsx (user-supplied)
- Process Map_ Project request process.png (user-supplied)

## Slide 2
DISCOVERY / CURRENT STATE
The problem is broken visibility—not a lack of tools
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
02
Work arrives through several channels, then loses a reliable owner, decision trail, or portfolio view.
Teams, Outlook, Jira, and Excel remain useful. The gap is a shared coordination layer that records who owns the next action, when it is due, and how it contributes to the customer-experience objective.
✓
Requests are scattered
✓
Approvals are hidden
✓
Ownership is inconsistent
✓
Delivery health is fragmented
✓
Benefits are not connected
Notes: [Sources]
- Phoenix Airlines discovery_asana.docx (user-supplied)

## Slide 3
SOLUTION / OPERATING MODEL
One goal connects intake, delivery, and adoption
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
03
The structure is deliberately small: one strategic connection, one leadership portfolio, and three purpose-built projects.
Asana object | Name | Role in the operating model
Goal | Improve customer experience and delivery reliability | Connect accepted initiatives to the business why
Portfolio | Customer Experience Transformation | Compare project health, timing, priority, and ownership
Project 1 | Biometric Boarding & Security Launch | Deliver a time-bound cross-functional launch
Project 2 | Project Request & Approval | Govern ongoing intake and decisions
Project 3 | Asana Adoption & Enablement | Train, launch, support, and improve
Notes: [Sources]
- Phoenix Airlines discovery_asana.docx (user-supplied)
- https://help.asana.com/s/article/monitor-initiatives-and-manage-resources-with-portfolios
- https://help.asana.com/s/article/plan-and-manage-company-goals

## Slide 4
WORKFLOW DESIGN / TYPE SELECTION
Deadline-bound and ongoing work need different patterns
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
04
DEADLINE-BOUND
Biometric launch
A defined start and finish. Sections act as phases; milestones mark gates; dependencies protect sequence; Timeline/Gantt exposes schedule risk.
ONGOING PROCESS
Project request approval
A repeatable flow with no fixed end date. Board sections show stage; a form standardizes intake; rules route work; decisions and SLAs protect accountability.
The Asana object is the same—a project—but the operating logic is different.
Notes: [Sources]
- Phoenix Airlines discovery_asana.docx (user-supplied)
- https://help.asana.com/s/article/task-dependencies
- https://help.asana.com/s/article/project-intake

## Slide 5
PROJECT 1 / DEADLINE-BOUND DELIVERY
Project 1 expands the source plan into a launch system
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
05
The source workbook supplied the delivery backbone. The capstone adds the controls needed for a credible biometric launch.
Privacy, security, training, pilot, go-live, hypercare, and benefits tracking are made explicit. Detailed engineering work can remain in Jira while Asana owns the cross-functional commitments and gates.
27
work items
10
milestones
29
dependency links
6
delivery phases
Notes: Counts describe the designed work plan, not completed business outcomes.
[Sources]
- Biometric Boarding and Security Project.xlsx (user-supplied)
- Phoenix_Airlines_Asana_Capstone_Workbook.xlsx (companion artifact)
- https://help.asana.com/s/article/import-csv-spreadsheets-into-projects

## Slide 6
PROJECT 1 / MILESTONES + DEPENDENCIES
The critical path protects every launch gate
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
06
The schedule moves through three accountable arcs. Each arc closes with explicit evidence before the next begins.
7–18 SEP
Research & select
Technology research → vendor selection → confirmed supplier
21 SEP–9 OCT
Comply & prepare
Regulatory, privacy, security, infrastructure, procurement, build, and training
13 OCT–6 NOV
Test, launch & learn
QA → security validation → pilot → go/no-go → go-live → benefits handover
Notes: [Sources]
- Biometric Boarding and Security Project.xlsx (user-supplied)
- Phoenix_Airlines_Asana_Capstone_Workbook.xlsx (companion artifact)
- https://help.asana.com/s/article/task-dependencies
- https://help.asana.com/s/article/plan-and-execute-projects-with-timeline

## Slide 7
PROJECT 2 / ONGOING INTAKE
Project 2 makes every request auditable
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
07
Asana preserves the decision gates and separates Approved, On Hold—Capacity, and Rejected outcomes for cleaner reporting.
Notes: Explain that On Hold—Capacity is a recommended improvement: a goal-aligned request without an available PM should remain visible instead of being lost as a rejection.
[Sources]
- Process Map_ Project request process.png (user-supplied)
- Phoenix Airlines discovery_asana.docx (user-supplied)

## Slide 8
PROJECT 2 / FORM + FIELDS
One form feeds routing, rules, and reporting
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
08
Required answers map to governed fields. Branching asks only the relevant sub-area question.
Question | Maps to | Decision value
Request title | Task title | Clear, outcome-focused record
Objective | Objective field / description | Goal-alignment evidence
Estimated budget | Currency field | Scoping and portfolio context
Improvement area | Shared single-select | Operations / Engineering / Technology routing
Conditional sub-area | Sub-area field | Ground, Flight, Mechanical, Software, Entertainment, or Security
Delivery date + attachment | Date + task attachment | Feasibility and supporting evidence
Notes: [Sources]
- Phoenix Airlines discovery_asana.docx (user-supplied)
- https://help.asana.com/s/article/project-intake
- https://help.asana.com/s/article/field-mapping-in-forms
- https://help.asana.com/s/article/how-to-use-forms-branching

## Slide 9
PROJECT 2 / AUTOMATION
Eleven rules automate movement—not accountability
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
09
Every automation is documented as a trigger, a condition, and an action. Ownership and decision rights remain visible.
TRIGGER
The event that starts evaluation
CONDITION
The criteria that must be true
ACTION
The accountable next step
Example: Goal Alignment changes → Yes → move to Resourcing Approval, update Status, and assign the accountable approver.
Rule groups: intake • functional routing • alignment decision • resource decision • kickoff • closure
Notes: [Sources]
- Phoenix_Airlines_Asana_Capstone_Workbook.xlsx (companion artifact)
- https://help.asana.com/s/article/rule-triggers
- https://help.asana.com/s/article/rule-actions
- https://help.asana.com/s/article/automate-how-work-moves-through-stages

## Slide 10
CHANGE NETWORK / ACCOUNTABILITY
Governance makes decision rights explicit
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
10
One accountable owner drives each decision; collaborators supply evidence and visibility.
Stakeholder | Capstone role | Primary accountability
Mark Thompson | Sponsor / workflow owner | Approve workflow changes and resourcing governance
Natalie Chang | Operations decision maker | Validate operational alignment and adoption
Ryan Patel | Technology approver | Review architecture, security, and integrations
Samantha Lewis | Benefits owner | Validate customer-experience alignment and measures
David Smith | Delivery lead / champion | Build, manage, train, and capture feedback
Notes: [Sources]
- Phoenix Airlines discovery_asana.docx (user-supplied)

## Slide 11
PROJECT 3 / SOCIALIZATION
Adoption is deployed as a workflow
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
11
The request workflow is the lead change case because it touches many teams and demonstrates visible value quickly.
25–31 AUG
Prepare
UAT, champion briefing, pre-launch email, and role-based training
1–4 SEP
Launch & support
Q&A, go-live, form link, daily hypercare, and issue triage
9 SEP–2 OCT
Measure & improve
Seven-day adoption review, baseline capture, and 30-day improvement backlog
Notes: [Sources]
- Phoenix Airlines discovery_asana.docx (user-supplied)
- Phoenix_Airlines_Asana_Capstone_Workbook.xlsx (companion artifact)
- https://help.asana.com/s/article/deploy-analyze-your-workflow

## Slide 12
MEASUREMENT / INITIAL TARGETS
Seven signals show whether the system is working
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
12
Targets are proposed for sponsor confirmation. The first two weeks establish the baseline; only then should improvement be claimed.
Signal | Initial target | Evidence
Complete intake rate | ≥95% | Form and required fields
Acknowledgment time | ≤1 business day | Created and assigned timestamps
Decision cycle time | ≤5 business days | Created and decision dates
Actionable-work rate | ≥95% | Assignee + due date completeness
On-time completion | ≥85% | Dashboard / reporting
Blocked-work age | <2 business days | Status history
30-day adoption | ≥80% | Weekly assigned-work activity
Notes: These are design targets, not achieved results.
[Sources]
- Phoenix_Airlines_Asana_Capstone_Workbook.xlsx (companion artifact)
- https://help.asana.com/s/article/project-dashboards
- https://help.asana.com/s/article/portfolio-progress-and-reporting

## Slide 13
QUALITY CONTROL / USER ACCEPTANCE TESTING
Ten UAT scenarios protect go-live
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
13
A workflow is not ready because it looks correct. It is ready when each branch, decision, permission, and report behaves as expected.
Every failure is fixed, evidenced, and retested. Test data is then archived or clearly labeled before the live form is shared.
✓
3 form branches
✓
2 alignment outcomes
✓
2 resourcing outcomes
✓
Permissions by role
✓
Dashboard reconciliation
Notes: [Sources]
- Phoenix_Airlines_Asana_Capstone_Workbook.xlsx (companion artifact)

## Slide 14
CERTIFICATE EVIDENCE / LEARNING OBJECTIVES
The capstone covers every specialist outcome
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
14
The strongest portfolio proof is not a long feature list. It is a traceable chain from business why to design, deployment, measurement, and expansion.
The final screenshots should show the build in Asana, while this case study explains the choices behind it.
✓
Collaborative Work Management
✓
Workflow type selection
✓
Discovery and process mapping
✓
Foundation + advanced build
✓
Deployment, measurement, expansion
Notes: [Sources]
- Phoenix Airlines discovery_asana.docx (user-supplied learning objectives)
- https://help.asana.com/s/article/deploy-analyze-your-workflow

## Slide 15
NEXT ACTION / PORTFOLIO COMPLETION
Build, test, then capture the proof
JAYSON • ASANA WORKFLOW SPECIALIST PORTFOLIO
15
The design is implementation-ready. The remaining evidence must come from Jayson’s own Asana workspace.
STEP 1
Build
Create the goal and portfolio, import Project 1, then configure Project 2 form, fields, and rules
STEP 2
Test
Run all UAT cases, fix duplicate or incorrect actions, and verify permissions and reporting
STEP 3
Prove
Capture the 12 recommended screenshots and add real measured results only when available
Start with Goal + Portfolio, then import the Project 1 sheet from the companion workbook.
Notes: [Sources]
- Phoenix_Airlines_Asana_Capstone_Portfolio.docx (companion artifact)
- Phoenix_Airlines_Asana_Capstone_Workbook.xlsx (companion artifact)