ASANA WORKFLOW SPECIALIST CAPSTONE Phoenix Airlines A governed request-to-delivery operating system in Asana Portfolio case study, implementation blueprint, and click-by-click build guide

THE PORTFOLIO PROOF

Two connected workflows turn fragmented intake, approval, execution, and adoption into visible, accountable work.

| Candidate | Scenario | Prepared |
| --- | --- | --- |
| Jayson | Phoenix Airlines — certificate capstone | 25 August 2026 |

Important This is a scenario-based portfolio design. Targets, owners by role, and future dates are implementation assumptions—not claimed production results.

# Executive summary

Phoenix Airlines wants to improve customer experience and become the highest-rated airline, but its project requests currently arrive through disconnected channels and become difficult to monitor after approval. This capstone creates a governed Asana operating model that connects intake, prioritization, resourcing, project delivery, portfolio oversight, and adoption.

| Portfolio component | Workflow type | Business result |
| --- | --- | --- |
| Biometric Boarding & Security Launch | Deadline-bound project | Plan, sequence, and monitor a cross-functional launch with milestones and dependencies. |
| Project Request & Approval | Ongoing process | Capture complete requests, review goal alignment, approve resources, and notify requesters consistently. |
| Deployment & Adoption | Change-management workstream | Prepare users, launch on 2 September 2026, measure adoption, and improve the workflow. |

Design principle Asana becomes the source of truth for ownership, stage, next action, due date, and delivery status. Teams, Outlook, Jira, and Excel remain purposeful supporting tools.

## How to use this portfolio

Use Parts 1–4 to explain your discovery, design decisions, and governance to an assessor or employer.

Follow the numbered build instructions in Parts 5–7 while creating the projects in Asana.

Use the companion workbook to import the biometric project and configure fields, rules, testing, and metrics.

Capture the recommended screenshots in Part 9 and place them in your final presentation or portfolio page.

# Contents

| Part | Topic |
| --- | --- |
| 1 | Discovery and the case for change |
| 2 | Governance, stakeholders, and success measures |
| 3 | Solution architecture and working conventions |
| 4 | Project 1 — Biometric Boarding & Security Launch |
| 5 | Project 2 — Project Request & Approval |
| 6 | Project 3 — Socialization, deployment, and adoption |
| 7 | Testing, reporting, and continuous improvement |
| 8 | Certificate response and portfolio narrative |
| 9 | Screenshot checklist and references |

PART 1

Discovery and the case for change

Ground the workflow in a clear business “why” before configuring Asana.

# 1.1 Business objective

Phoenix Airlines aims to improve customer experiences and satisfaction and ultimately become the number-one rated airline. The work-management opportunity is to make every initiative traceable from request to business goal, then visible through delivery and benefits review.

## 1.2 Current-state diagnosis

| Observed challenge | Root cause | Operational effect | Asana design response |
| --- | --- | --- | --- |
| Requests are submitted manually through several tools. | No standard intake channel or required data model. | Missing information, duplicate follow-up, and slower review. | One form maps answers to governed custom fields and creates a task in New Request. |
| Approvals and resource decisions are difficult to trace. | Decision criteria, owner, and status are not centralized. | Requests stall or are approved inconsistently. | Explicit review stages, decision fields, approval tasks, due dates, and rules. |
| Projects lose visibility after kickoff. | No connected portfolio view or consistent status update cadence. | Leadership cannot compare health, risk, and timing. | Connected portfolio, project status updates, milestones, dashboards, and a shared goal. |
| Teams rely on memory for next actions. | Ownership and due-date conventions are weak. | Lead time and accountability deteriorate. | Every active task has one assignee, one due date, and a specific next action. |

## 1.3 Tool-stack decision

| Tool | Keep it for | Do not use it as |
| --- | --- | --- |
| Asana | Work intake, ownership, stage, dependencies, approvals, status, dashboards, portfolios, goals. | A file repository for every working document or a replacement for specialized engineering issue tracking. |
| Microsoft Teams | Live collaboration, meetings, and rapid discussion. | The authoritative record of project status or approval. |
| Outlook | Formal external email and calendar invitations. | A hidden task list or approval archive. |
| Jira | Detailed software defects, stories, and engineering execution where already established. | The enterprise intake front door for all business projects. |
| Excel | Financial models, detailed analyses, and controlled data calculations. | The live workflow tracker once work is accepted into Asana. |

Decision rule If information changes who owns work, what happens next, or when it is due, update Asana. Link to supporting Teams, Jira, Outlook, or Excel records instead of duplicating the workflow.

## 1.4 Scope and assumptions

The organizational Asana go-live date is assumed to be 2 September 2026 because the discovery document specifies 2 September without a year.

The biometric project is rescheduled into a future demonstration window beginning 7 September 2026; the original workbook’s task logic is preserved and expanded.

Role-based owners are used where a named delivery specialist is not supplied. Replace placeholders before publishing the live project.

Approvals, branching, portfolios, goals, workload, and some dashboards depend on the organization’s Asana plan. A custom-field fallback is included.

PART 2

Governance, stakeholders, and success

Make ownership, decision rights, and evidence of value explicit.

# 2.1 Change network

| Stakeholder | Role in the capstone | Primary responsibility |
| --- | --- | --- |
| Mark Thompson — Director, PMO | Executive sponsor / workflow owner | Approves workflow changes, resourcing governance, and operating conventions. |
| Natalie Chang — Operations Manager | Decision maker / operations champion | Confirms operational alignment and supports adoption across ground and flight teams. |
| Ryan Patel — IT Director | Technology approver | Reviews architecture, security, integrations, and technology requests. |
| Samantha Lewis — Head of Customer Experience | Benefits owner | Validates customer-experience alignment and outcome measures. |
| David Smith — Project Manager | Delivery lead / Asana champion | Builds and manages the biometric launch; supports peer training and feedback. |
| Requesters and functional PMs | Workflow participants | Submit complete requests, respond to clarification, and maintain accepted delivery work. |

## 2.2 RACI for the request workflow

| Activity | PMO | Functional reviewer | Requester | Assigned PM | Sponsor |
| --- | --- | --- | --- | --- | --- |
| Submit request | I | I | R/A | — | I |
| Check completeness | R/A | C | C | — | I |
| Assess goal alignment | R | C | C | — | A |
| Confirm PM availability | R | C | I | C | A |
| Approve / hold / reject | R | C | I | I | A |
| Kick off accepted project | C | C | I | R/A | I |
| Report portfolio status | R | C | I | C | A |

R = Responsible, A = Accountable, C = Consulted, I = Informed.

## 2.3 Initial success measures

| Measure | Definition | Initial target | Data source |
| --- | --- | --- | --- |
| Complete intake rate | Requests with every required field and supporting evidence. | ≥95% | Form and custom fields |
| Acknowledgment time | Business time from submission to PMO ownership. | ≤1 business day | Created and assigned timestamps |
| Decision cycle time | Business days from submission to approved, on hold, or rejected. | ≤5 business days | Created date and decision date |
| Actionable-work rate | Active tasks with both assignee and due date. | ≥95% | Project search / dashboard |
| On-time completion | Completed tasks finished by due date. | ≥85% | Dashboard / reporting |
| Blocked-work age | Average time a task remains blocked. | <2 business days | Status and activity history |
| Adoption | Target users completing assigned Asana work weekly. | ≥80% after 30 days | Usage/reporting data |

Measurement discipline These are implementation targets. Record the first two weeks as the baseline, then confirm or revise targets with the sponsor at the 30-day review.

PART 3

Solution architecture and conventions

Connect intake, delivery, goals, and reporting without duplicating work.

# 3.1 Recommended Asana structure

| Asana object | Name | Purpose |
| --- | --- | --- |
| Goal | Improve customer experience and delivery reliability | Strategic connection for accepted initiatives; use a qualitative or metric-based update agreed with the sponsor. |
| Portfolio | Customer Experience Transformation | Leadership view of project health, priority, owner, timing, and goal contribution. |
| Project 1 | Biometric Boarding & Security Launch | Deadline-bound delivery project with dependencies, milestones, approvals, and status reporting. |
| Project 2 | Project Request & Approval | Ongoing intake and decision workflow managed as a board. |
| Project 3 | Asana Adoption & Enablement | Go-live communication, training, support, and measurement plan. |

## 3.2 Shared custom-field governance

| Shared field | Values / format | Owner | Usage rule |
| --- | --- | --- | --- |
| Priority | High / Medium / Low | PMO | Reflects business urgency and impact—not requester preference alone. |
| Work Status | Not Started / In Progress / Blocked / At Risk / Complete | PMO | Used across delivery projects; update before weekly status review. |
| Project Size | Small / Medium / Large | PMO | Set during scoping using agreed effort/budget thresholds. |
| Improvement Area | Operations / Engineering / Technology | PMO | Form-mapped; determines routing and reporting. |
| Decision | Pending / Approved / On Hold / Rejected | PMO | Only the accountable approver or delegated PMO reviewer changes it. |
| Risk Level | Low / Medium / High / Critical | Project manager | Review weekly and whenever a blocker affects a milestone. |

## 3.3 Working conventions

Task names begin with an action verb and describe one outcome: “Approve security architecture,” not “Security.”

Every active task has one accountable assignee and a realistic due date. Collaborators support; they do not replace accountability.

Use task descriptions for scope, definition of done, links, and decision criteria. Use comments for dated updates and decisions.

Use subtasks only when a parent outcome requires distinct owners or due dates; otherwise use a checklist in the description.

Milestones represent zero-duration achievements or decision gates. Dependencies represent work that must finish before another task can start.

Update project status weekly using the same health language: On track, At risk, Off track, or Complete.

Do not create duplicate trackers. Multi-home a task or link the authoritative record when work must appear in more than one view.

PART 4

Project 1 — Biometric Boarding & Security Launch

A deadline-bound project that demonstrates milestones, dependencies, approvals, custom fields, and portfolio reporting.

# 4.1 Project charter

| Element | Definition |
| --- | --- |
| Purpose | Launch a secure, compliant biometric boarding capability that improves passenger flow while protecting personal data. |
| Project owner | David Smith, Project Manager |
| Executive stakeholders | Ryan Patel, Samantha Lewis, Natalie Chang, and Mark Thompson |
| Demonstration schedule | 7 September–6 November 2026 |
| Definition of done | Technology selected; compliance, privacy, and security approved; infrastructure and integration ready; testing and pilot accepted; go-live completed; handover and benefits tracking initiated. |
| Out of scope | Detailed software backlog and defect management, which may remain in Jira and link back to Asana milestones. |

## 4.2 Sections and stage gates

| Section | Exit milestone |
| --- | --- |
| Initiation & Research | Research and analysis complete |
| Vendor & Compliance | Vendor confirmed; regulatory and security approvals complete |
| Infrastructure & Procurement | Infrastructure and integration environment ready |
| Build & Integration | Build complete |
| Testing & Pilot | Testing and pilot accepted |
| Launch & Handover | Production go-live; benefits tracking begins |
| Complete | Project closeout approved |

## 4.3 Import and enrich the work plan

The companion workbook contains an import-ready “P1 Asana Import” sheet. It preserves every source-workbook activity and milestone, separates dependency logic from task names, supplies role-based owners, and adds privacy, training, pilot, go-live, and handover work required for a credible product launch.

Prepare the file — Open the companion workbook, review role placeholders and dates, then export only the “P1 Asana Import” sheet as CSV UTF-8 if your Asana workspace requires CSV.

Create the project — In Asana, select Create → Project → Blank project; name it “Biometric Boarding & Security Launch”; choose List as the default view; set privacy to the intended project team.

Import the plan — Open the project menu beside the project name and choose Import → CSV (or use Create → Project → Import spreadsheet). Select the prepared file.

Map columns — Map Task Name, Section, Assignee, Due Date, and Description. Map Priority, Work Status, Workstream, Risk Level, and Task Type to custom fields.

Review before import — Confirm that each row previews as one task, dates are recognized, and no field accidentally maps to the task title.

Complete the import — Inspect all sections, dates, owners, descriptions, and custom-field values. Correct any placeholder owners before inviting the full team.

## 4.4 Configure milestones and dependencies

Mark milestones — Filter Task Type = Milestone. Open each matching task, use the task-type menu, and select Mark as milestone.

Open Timeline or Gantt — Add the view if it is not already visible. Confirm the schedule reads left to right by phase.

Add dependencies — For each row on the “P1 Dependencies” sheet, open the successor task and add the listed predecessor under Dependencies; alternatively drag dependency connectors in Timeline.

Check the critical sequence — Vendor confirmation, compliance/security approval, infrastructure readiness, build, testing, pilot, launch readiness, and go-live should form an unbroken chain.

Resolve date conflicts — If a predecessor ends after its successor is due, move the successor and any affected downstream work. Document the decision in a comment.

Dependency example “Testing and QA” cannot start until “Build complete.” The milestone records the achievement; the dependency enforces the sequence.

## 4.5 Add project-level custom fields

| Field | Type | Values / use |
| --- | --- | --- |
| Priority | Single select | High / Medium / Low |
| Work Status | Single select | Not Started / In Progress / Blocked / At Risk / Complete |
| Workstream | Single select | PMO / Technology / Security / Compliance / Operations / Customer Experience / Vendor |
| Risk Level | Single select | Low / Medium / High / Critical |
| Budget Health | Single select | Not Assessed / On Budget / Watch / Over Budget |
| Task Type | Single select | Task / Milestone / Approval |

Open Customize — Select Customize in the project header, then Add field.

Reuse shared fields — Search the organization field library first. Reuse governed Priority, Work Status, and Risk Level fields rather than creating duplicates.

Create project-specific fields — Add Workstream, Budget Health, and Task Type only if equivalent fields do not exist.

Order the fields — Place Work Status, Priority, Workstream, Risk Level, and Due Date near the left side of List view for fast scanning.

## 4.6 Recommended rules

| Trigger | Condition | Action |
| --- | --- | --- |
| Work Status changes | Blocked | Set Risk Level to High; add the project manager as collaborator; post a blocker-resolution comment template. |
| Due date is approaching | Incomplete and due within 3 days | Notify assignee and add “Confirm completion forecast” subtask. |
| Task moves to Testing & Pilot | Workstream = Technology or Security | Add QA/security reviewer as collaborator and set Work Status to Not Started. |
| Approval outcome changes | Request changes or Rejected | Set Work Status to Blocked; move to the appropriate section; notify project manager. |
| Task completed | Task Type = Milestone | Post a comment prompting a project-status update and downstream review. |

Build each rule through Customize → Rules → Add rule. Choose a trigger, add conditions, then add one or more actions. Test the rule on a noncritical sample task before publishing it.

## 4.7 Configure the project overview and views

Overview — Add the purpose, scope, definition of done, project owner, stakeholder roles, key resources, and communication cadence.

List — Save a working view grouped by Section and sorted by Due Date.

Timeline or Gantt — Display dependencies and color by Workstream or Risk Level.

Calendar — Show launch, training, pilot, and go-live dates for operational stakeholders.

Dashboard — Add charts for tasks by Work Status, tasks by Workstream, overdue tasks by assignee, milestones by completion, and risk level.

Status updates — Schedule a weekly Friday reminder for the project owner to publish health, accomplishments, blockers, and next steps.

## 4.8 Connect the project to strategy

Add to portfolio — Open “Customer Experience Transformation,” choose Add work, and select the biometric project.

Set portfolio fields — Populate Priority, Sponsor, Health, Target Launch, Budget Health, and Customer Impact.

Connect the goal — From the project Overview or the goal page, connect the project to “Improve customer experience and delivery reliability.”

Define progress — Use project status or a sponsor-approved metric as the goal’s progress source; avoid claiming benefits before measurement begins.

PART 5

Project 2 — Project Request & Approval

An ongoing intake workflow that converts a process map into a governed board, form, decisions, and automations.

# 5.1 Translate the process map into Asana

Figure 1 — Supplied project-request approval process map used as the design baseline.

The supplied map uses New Request → Assigned → In Review → Resourcing Approval → Completed. The Asana design preserves those controls and separates successful kickoff from terminal rejection so reporting remains unambiguous.

| Process-map stage | Asana section | Exit condition |
| --- | --- | --- |
| New Request | New Request | Required data is present and a PMO reviewer owns the task. |
| Assigned | Assigned | Reviewer begins assessment. |
| In Review | In Review | Goal alignment is recorded. |
| Resourcing approval | Resourcing Approval | PM availability and decision are recorded. |
| Completed — approved path | Approved — Kickoff | Requester is notified, PM assigned, and delivery project created. |
| Completed — no path | Rejected — Closed | Decision reason is documented and requester notified. |
| Recommended improvement | On Hold — Capacity | Goal-aligned demand without an available PM is retained for later review instead of being lost as a rejection. |
| Archive | Completed | All workflow closure actions are complete. |

## 5.2 Create the board foundation

Create the project — Select Create → Project → Blank project; name it “Project Request & Approval”; select Board view; assign Mark Thompson or the designated PMO owner as project owner.

Add sections — Create New Request, Assigned, In Review, Resourcing Approval, Approved — Kickoff, On Hold — Capacity, Rejected — Closed, and Completed in that order.

Set project access — Give PMO editors permission to update workflow fields; give broader stakeholders comment or view access as appropriate.

Write the Overview — Add the purpose, eligibility, decision criteria, SLA, owners, and links to the intake form and policy.

## 5.3 Add workflow fields

| Field | Type | Values / mapping |
| --- | --- | --- |
| Request Title | Task title | Short, outcome-focused title supplied by requester. |
| Objective | Long text | What the project will change and why. |
| Estimated Budget | Number / currency | Requester estimate; validate during review. |
| Improvement Area | Single select | Operations / Engineering / Technology |
| Sub-area | Single select | Ground / Flight / Mechanical / Software / Entertainment / Security |
| Project Delivery Date | Date | Map to due date or a dedicated target-date field. |
| Project Size | Single select | Small / Medium / Large |
| Priority | Single select | High / Medium / Low |
| Status | Single select | New / Assigned / In Review / Resourcing Approval / Approved / On Hold / Rejected / Completed |
| Goal Alignment | Single select | Pending / Yes / No |
| PM Availability | Single select | Pending / Yes / No |
| Decision | Single select | Pending / Approved / On Hold / Rejected |
| Decision Reason | Text | Required before hold or rejection is communicated. |

## 5.4 Build the request form

Open Forms — In the project, select Customize → Forms → Create form.

Name and explain — Title it “Phoenix Airlines Project Request.” Explain eligibility, expected response time, and that complete evidence accelerates review.

Add Request Title — Use a short-answer question and map it to the task title.

Add required questions — Objective; Estimated Budget; Improvement Area; Project Delivery Date; and Supporting Data attachment.

Add branching — If Operations, ask Ground or Flight. If Engineering, ask Mechanical or Software. If Technology, ask Entertainment or Security.

Map answers — Map Improvement Area, Sub-area, Estimated Budget, and Project Delivery Date to their matching fields; map the date to the task due date only if it truly represents the workflow deadline.

Set routing — Choose New Request as the destination section and the PMO intake owner as default assignee.

Confirmation message — State that the PMO will acknowledge the request within one business day and will communicate approved, on-hold, or rejected status in Asana/email.

Publish and test — Submit one request for each branch and verify the created tasks before sharing the link.

Plan-aware fallback If form branching is unavailable, show one Sub-area question with all six values and include short helper text explaining which values apply to each Improvement Area.

## 5.5 Build the automations

| # | Trigger | Condition | Action |
| --- | --- | --- | --- |
| 1 | Task added to New Request | Created by form | Assign PMO intake owner; set Status = New; set review due date; add acknowledgment subtask. |
| 2 | Task moves to Assigned | Incomplete | Set Status = Assigned; assign PMO reviewer. |
| 3 | Improvement Area changes | Technology | Add IT Director or technology reviewer as collaborator. |
| 4 | Improvement Area changes | Operations | Add Operations Manager as collaborator. |
| 5 | Task moves to In Review | Incomplete | Set Status = In Review; create “Validate goal alignment” subtask. |
| 6 | Goal Alignment changes | No | Set Decision = Rejected; move to Rejected — Closed; create notification/decision-reason subtask. |
| 7 | Goal Alignment changes | Yes | Move to Resourcing Approval; set Status = Resourcing Approval; assign accountable approver. |
| 8 | PM Availability changes | Yes | Set Decision = Approved; move to Approved — Kickoff; create kickoff subtasks. |
| 9 | PM Availability changes | No | Set Decision = On Hold; move to On Hold — Capacity; create capacity-review date and notification subtask. |
| 10 | Task moves to Approved — Kickoff | Decision = Approved | Create “Assign PM,” “Notify requester,” “Create delivery project,” and “Schedule kickoff” subtasks. |
| 11 | Task completed | Section is terminal | Move to Completed and set Status = Completed. |

Open the rule builder — Customize → Rules → Add rule.

Choose the trigger — Select task added, section changed, custom field changed, approval status changed, or due-date trigger.

Add conditions — Restrict the rule to the relevant field value or section so it does not fire on unrelated work.

Add actions — Assign, change fields, move sections, set dates, add collaborators, create tasks/subtasks, or post a comment.

Name clearly — Use “R07 — Goal aligned → Resourcing Approval,” matching the companion rule register.

Test and publish — Use a sample request and confirm every field, assignee, task, and notification before activating the rule.

## 5.6 Add formal approvals

If the workspace includes approval tasks, use one approval at Goal Alignment and a second at Resourcing Approval. The approver chooses Approved, Request changes, or Rejected, and outcome-based rules update fields and sections. If approvals are unavailable, use the Goal Alignment, PM Availability, and Decision custom fields with the same rule logic; the governance remains intact.

## 5.7 Reporting and portfolio connection

Dashboard — Add request count by Status, requests by Improvement Area, decisions by outcome, overdue reviews by assignee, and requests by Priority and Project Size.

Cycle time — Report created-to-decision duration using reporting/date fields available on your plan; otherwise export monthly timestamps for calculation.

Portfolio — Add the ongoing intake project to “Customer Experience Transformation” so leadership can access its status and dashboard.

Goal — Connect only approved delivery projects—not rejected requests—to the customer-experience goal. Keep the intake project connected as the governance mechanism if useful.

Monthly review — Review capacity-held demand, repeated rejection reasons, SLA misses, and field completeness to improve policy and staffing.

PART 6

Project 3 — Socialization, deployment, and adoption

Deploy the Project Request & Approval workflow as the lead change case for the 2 September 2026 go-live.

# 6.1 Deployment strategy

The request workflow is the best socialization candidate because it affects many teams, replaces visible manual handoffs, and demonstrates forms, fields, rules, approvals, dashboards, portfolios, and goals in one process.

| Date | Audience | Activity | Owner | Evidence |
| --- | --- | --- | --- | --- |
| 25 Aug | PMO + champions | Configuration review and UAT kickoff | David / PMO | Signed UAT checklist |
| 26–27 Aug | Change Network | Champion briefing and scenario practice | Mark | Questions log and champion readiness |
| 28 Aug | All requesters | Pre-launch email with why, date, and expectations | Samantha | Email and intranet post |
| 31 Aug | PMO + approvers | Role-based live training and rule walkthrough | David | Attendance and practice tasks |
| 1 Sep | All users | Open Q&A and office hours | Champions | FAQ updates |
| 2 Sep | Organization | Go-live announcement and form link | Mark | Published workflow and support channel |
| 3–4 Sep | Users | Hypercare and daily triage | PMO + champions | Issue log and fixes |
| 9 Sep | Leadership | Seven-day adoption and SLA review | Mark | Dashboard snapshot |
| 2 Oct | Sponsor + PMO | Thirty-day value and improvement review | Mark | Baseline/target comparison and backlog |

## 6.2 Role-based training

| Audience | Must be able to do | Practice scenario |
| --- | --- | --- |
| Requesters | Open form, submit complete evidence, find the request, respond to questions, interpret status. | Submit a Technology → Security request and reply to a clarification. |
| PMO reviewers | Triage, assign, assess completeness, update fields, apply decision criteria, meet SLA. | Move a complete request from New to In Review. |
| Approvers | Review evidence, approve/request changes/reject, record rationale, avoid out-of-band decisions. | Reject a nonaligned request with a clear reason. |
| Project managers | Accept approved work, create delivery project, set milestones/dependencies, report status. | Convert an approved request into a kickoff plan. |
| Leaders | Read portfolio health, dashboard measures, capacity-held demand, and status updates. | Identify one at-risk project and one bottleneck. |

## 6.3 Communication draft

Subject: A simpler way to request and approve projects—launching 2 September From 2 September, submit new project requests through the Phoenix Airlines Project Request form. The new Asana workflow gives every request an owner, visible status, decision trail, and next action. PMO will acknowledge complete submissions within one business day. Join the 31 August training or 1 September Q&A, and use the published support channel for help after launch.

## 6.4 Go-live checklist

□ Sponsor approves workflow, SLA, fields, decision criteria, and fallback process.

□ Form branch tests pass for Operations, Engineering, and Technology.

□ Rules pass UAT without duplicate assignments, moves, or notifications.

□ Project permissions and form-sharing settings are verified.

□ PMO and approvers complete role-based training.

□ Help article, form link, support channel, and escalation path are published.

□ Dashboards display test data correctly; sample data is archived or labeled.

□ Hypercare owners and daily review times are assigned.

□ Seven-day and 30-day review meetings are scheduled.

PART 7

Testing, reporting, and continuous improvement

Prove the workflow works before launch and use data to improve it after launch.

# 7.1 Minimum UAT scenarios

| Scenario | Expected result |
| --- | --- |
| Submit Operations → Ground request | Task appears in New Request with mapped fields, attachment, assignee, review due date, and acknowledgment task. |
| Submit Engineering → Software request | Correct Sub-area is recorded and relevant reviewer can access the task. |
| Submit Technology → Security request | IT/security stakeholder is added and all evidence remains attached. |
| Mark Goal Alignment = No | Task moves to Rejected — Closed, Decision = Rejected, and notification/reason task is created. |
| Mark Goal Alignment = Yes | Task moves to Resourcing Approval and accountable approver owns the next decision. |
| Mark PM Availability = Yes | Request moves to Approved — Kickoff and all four kickoff subtasks are created once. |
| Mark PM Availability = No | Request moves to On Hold — Capacity with a review date and requester-notification task. |
| Complete terminal workflow task | Task moves to Completed and Status = Completed without re-triggering earlier rules. |
| Delay biometric predecessor task | Successor remains visibly blocked and schedule conflict is obvious in Timeline/Gantt. |
| Complete biometric milestone | Downstream assignees receive dependency notification and status reporting is prompted. |

## 7.2 Dashboard interpretation

| Signal | Question to ask | Likely action |
| --- | --- | --- |
| Many New Requests older than one day | Is PMO capacity or assignment logic failing? | Rebalance intake ownership or adjust the assignment rule. |
| High rejection rate for one Improvement Area | Are eligibility or form instructions unclear? | Clarify criteria and add examples to the form. |
| Large On Hold — Capacity queue | Is staffing aligned with demand? | Prioritize portfolio demand or secure additional PM capacity. |
| Frequent Blocked biometric tasks | Which dependency or reviewer is the bottleneck? | Escalate the gate, change sequencing, or add capacity. |
| Low weekly activity | Did users understand conventions and value? | Target coaching, office hours, and champion follow-up. |

## 7.3 Improvement cadence

Weekly — PMO reviews aged intake, pending approvals, and rule exceptions.

Fortnightly — Project managers review milestone health, blockers, and portfolio status quality.

Monthly — Sponsor reviews SLA, decision mix, capacity-held demand, adoption, and field completeness.

Quarterly — Workflow owner evaluates form questions, field library, rules, templates, integrations, and training content.

Before any change — Test in a sandbox/sample project, document the reason, name the owner, and communicate the change.

PART 8

Certificate response and portfolio narrative

Turn the build into concise evidence of workflow-specialist capability.

# 8.1 Best-practice response (80 words)

Certificate submission Shared custom fields are the best practice I would prioritize because they make the same business meaning visible across both Phoenix Airlines workflows. A governed Status, Priority, Improvement Area, and Risk field lets rules, dashboards, and portfolios report consistently instead of relying on free-text updates. I would place approved fields in the organization’s field library, define each value, and restrict who can change the schema. This improves adoption, automation reliability, and executive reporting while still allowing each project to keep workflow-specific fields.

## 8.2 STAR-style portfolio story

| Element | Interview narrative |
| --- | --- |
| Situation | Phoenix Airlines had fragmented project intake, slow decisions, and limited visibility after kickoff. |
| Task | Design an Asana operating model that supports both a deadline-bound biometric launch and an ongoing request-approval process. |
| Action | Mapped the process, clarified the why and tool stack, created governed fields and forms, designed rules and approvals, connected projects to a portfolio and goal, and planned UAT and adoption. |
| Result | Produced an implementation-ready blueprint with measurable targets. In a live deployment, the next step is to establish the baseline and validate whether cycle time, completeness, and adoption improve. |

Evidence standard Do not present simulated targets as achieved results. After building in Asana, replace design screenshots with your own workspace evidence and add real measured outcomes only when available.

## 8.3 Skills demonstrated

Collaborative Work Management: one cross-functional source of truth with explicit ownership and handoffs.

Workflow selection: deadline-bound product launch and ongoing intake/approval process.

Discovery: business why, current tools, stakeholders, constraints, and success measures.

Workflow design: process mapping, clarifying questions, stage gates, decisions, and exception handling.

Asana build: projects, sections, forms, custom fields, milestones, dependencies, approvals, rules, dashboards, portfolios, and goals.

Deployment: communications, training, conventions, UAT, hypercare, and change network.

Measurement and expansion: SLA, cycle time, adoption, portfolio reporting, and improvement cadence.

PART 9

Screenshot checklist and references

Capture credible evidence after you reproduce the design in your own Asana workspace.

# 9.1 Portfolio screenshot checklist

| # | Screenshot | What it should prove |
| --- | --- | --- |
| 1 | Goal page with connected work | The project is linked to a business outcome. |
| 2 | Customer Experience Transformation portfolio | Leadership can see owner, health, priority, and target date. |
| 3 | Biometric project List view | Sections, owners, dates, fields, and milestones are complete. |
| 4 | Biometric Timeline/Gantt | Dependencies and stage sequence are visible. |
| 5 | Biometric Dashboard | Status, risk, workstream, overdue work, and milestone completion are reportable. |
| 6 | Project Request board | The ongoing process has clear stages and terminal outcomes. |
| 7 | Published request form | Required questions and professional instructions are visible. |
| 8 | One branching path | Improvement Area correctly controls Sub-area questions. |
| 9 | Rule builder | A named trigger–condition–action rule is configured. |
| 10 | Approval or decision task | Decision rights and outcomes are traceable. |
| 11 | Request workflow Dashboard | Cycle, volume, status, priority, and decision patterns are visible. |
| 12 | Adoption project or communication plan | Deployment and measurement are treated as work, not an afterthought. |

## 9.2 Build-completion checklist

□ Companion workbook reviewed and role placeholders replaced.

□ Biometric tasks imported and all milestones manually marked.

□ Dependencies tested by completing a predecessor task.

□ Request form tested across all three Improvement Area branches.

□ Every rule passes UAT once and does not create duplicate actions.

□ Projects are added to the portfolio and connected to the goal.

□ Dashboards display meaningful test data.

□ Socialization tasks, owners, and due dates are created.

□ Screenshots contain no confidential or personal data.

□ Final presentation explains design choices and clearly labels projected outcomes.

## 9.3 Source materials

Phoenix Airlines discovery_asana.docx — supplied discovery brief and capstone requirements.

Biometric Boarding and Security Project.xlsx — supplied reference task plan.

Process Map_ Project request process.png — supplied project-request approval process map.

## 9.4 Official Asana implementation references

Project intake

CSV spreadsheet imports

Field mapping in forms

Form branching

Rule triggers

Rule actions

Automating work through stages

Task dependencies

Timeline planning

Approvals

Project dashboards

Portfolio monitoring

Planning and managing goals

Project overview

Deploy and analyze a workflow

Plan availability Asana feature availability and menu labels can vary by plan and product updates. Validate Forms branching, Approvals, Portfolios, Goals, Workload, and reporting access in the workspace used for the capstone.